## Sheet1
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1 | As a member, I can view tasks and recommendations(depending on my skills) to apply for it | 6 | karim | Depending on partner requested a task with my skills | partner requested a task with certiane skills I will sow them
2 | As a member, I can apply for a task | 6 | karim | there is atask on not | select task to apply for it
3 | As a member, I can show my notification | 6 | karim | if I accepted in certain task | accepted by admin in a task
4 | As a partner, I can Delete my co-working space or my Conultancy agency or my education center | 6 | karim | create any entity related with partner | show my entities as a partner after deletion
5 | As a partner, I can request and fill a form for a job supported with description and mentioning consulting agency needed or not | 4 | ahemd hashem
6 | As a partner , I can receive acceptance for my description | 4 | ahmed hashem | if admin accpted my project | accept or reject the projecct by admin
7 | As a partner, I can receive acceptance for my task by a member | 4 | ahmed hashem | admin assing of the admin | admin assign certine member to my project
8 | As a partner , I can receive my task after finishing | 4 | ahmed hashem | send project from member | member update the task with file or link
9 | As an admin, I can accept or reject task | 8 | abdelrahman badr | partner requested atask | accept or reject the project
10 | As an admin, I can post the accepted description so that A member can apply for it | 8 | abdelrahman badr | there is atask and I accpted it | accept a task and post it
11 | As an admin, I can view form submitted by partners to post it on the platform | 8 | abdelrahman badr | apartner fill ther form | a partner fill the form and I checked it
12 | As an admin, I can decide who will be assigned for a task to begin working on it based on his skills and the task’s specifications | 8 | mahmoud eslam | apply for aproject by member | check members skills and assing one of thme to the project
13 | As an admin, I can view a list of candidate members of specific task to choose the best one of them | 8 | mahmoud eslam | member apply fo projct | get the members for tasks applied list
14 | As a member, I can update the cycle of the task to inform the partner with the progress | 6 | marina | I accpeted in that project | I change the value of the project cycle
15 | As a User in Lertinhub, I can request for editing my profile if accepted upadte it | 6 | marina | I created profile | change anything in my profile and show the change
16 | As a User in Lertinhub, I can show my profile | 6 | marina | I created profile | select my profile
17 | As a partner, I can delete or edit my requested job if not posted yet | 4 | mayar | there is aproject which I requested | request the change form the admin
18 | As a partner, I can show cycle of the project | 4 | mayar | updating the cycle by the member | the memebr change the cycle
19 | As a partner , I can give feedback or a report about the task | 4 | mayar | member upload the file | give feedback or rate and show the change in the membre rate
20 | As a partner, I can create a profile for consulting agency | 4 | abdelrahman khaled | nothing | create a profile and show it
21 | As a partner , I can post studies reports on my consulting agency profile | 4 | abdelrahman khaled | nothing | upload the reports
22 | As a partner, I can show all jobs that needed consults as a consulting agency | 4 | abdelrahman khaled | requtes a consult on a certine task | show the tasks hat consult is need in the task
23 | As a partner, I can give feedback and high description and financial details and timing as a consulting agency | 4 | abdelrahman khaled | consultancy needed in atask | set theses fielde with the new values
24 | As a partner, I can view all possible consults of my task | 4 | mayar | consulty is give feed back to back my task | show the consulty feedback
25 | As an admin, I can view task cycle to enable the partner to show his task progress | 8 | mahmoud eslam | member update the work cycle | member update the work cycle
26 | As an admin, I can view a list of all members and all partners. | 6 | mahmoud hashem | member and partner create profile | slecet the member and parter
27 | As an admin, I can ban or delete a post | 6 | mahmoud hashem | upload post | delete it
28 | As an admin, I can ban or delete a member | 6 | mahmoud hashem | member create profile | delete it
29 | As an admin, I can approve or reject any request of editing. | 6 | mahmoud hashem | member or partner request the change | accept or reject that change
30 | As a partner, I can accept one of consults related to my job | 4 | orabi | consultancy give feed back to my task | slecet one of them
31 | As a partner owner to consultancy agency, I can view notifications from partner as accepted my consult | 4 | orabi | anotther parrtner accept consultancy agency | make an partner accept consultancy and show the change
32 | As a member, I can apply for courses to enhance my skills | 6 | marina | nothing | slecet course and apply for it and show the change in my profile
33 | As a member, I can communicate with experts to get recommendations for masterclasses | 6 | nada | nothing | post need info to make expert give recommendation
34 | As a member, I can give recommendations to other members | 6 | nada | thereis amember that request a recommeendation | give a recommend to the post
35 | As a member, I can give rate to certain recommendations | 6 | nada | there is arecommendation from expert | give rate to recomminadtion and show the change
36 | As a member, I can receive rate on my recommendations | 6 | nada | member gives rate | show the change in my rate or post rate
37 | As a partner, I can create profile for my coworking space(giving info about the location , available slots ,show business plans). | 4 | ahemd hashem | nothing | create the profile with info
38 | As a partner, I can show all info about rooms of specific co-working space such as reservation details | 4 | ahmed hashem | create co working space | slecet the coworking space and display its info
39 | As a partner, I can create an account as an educational organization | 4 | orabi | nothing | create the profile with info
40 | As a partner, I can offer courses and masterclasses, give information about available places and prices | 4 | orabi | create educational center | fill courses details and info about them
41 | As a partner, I can accept students for my educational organization | 4 | orabi | member apply for cousres | set the acepptance value for the member
42 | As a partner, I can CRUD information about educators and trainers | 4 | orabi | there is a education center | manipulate with his info
43 | As a partner, I can reserve workshop for a course as an educational organization | 4 | mayar | create a working space | set the reservation time and show that change in co working space data
44 | As a partner, I can notify the system that a certain member completes a certain course | 4 | mayar | nothing | show to the system that member complete the course to set that in this profile
45 | As a partner, I can add rooms info to my co-working space | 4 | abdelrahman khaled | there is a co working space | show that change in coworking spavce info
46 | As a partner, I can accept reservations of rooms on coworking spaces | 4 | abdelrahman khaled | partner reserve coworking space | set the accetance value and show the change