## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1 | update the CRUD of admin By Mongo | 5 | Abdelrahman Badr | Mahmoud Hashem | Mahmoud Eslam
1.1 | update the CRUD of partner By Mongo | 5 | Marina | Karim Tamir | Nada
1.2 | update the CRUD of member By Mongo | 5 | Marina | Karim Tamir | Nada
1.3 | update the CRUD of Consultancy Agency By Mongo | 5 | Abdelrhman Khaled | Ahmed Hashem | Mayar
1.4 | update the CRUD of Coworking Space By Mongo | 5 | Ahmed Hashem | Abdelrahman Khaled | Orabi
1.5 | update the CRUD of educational Center By Mongo | 5 | Mayar | Orabi | Ahmed Hashem
1.6 | update the CRUD of projects By Mongo | 5 | karim Tamer | nada | Marina
1.7 | update the CRUD of Courses By Mongo | 5 | Mayar | Ahmed Hashem | Abdelrhman Khaled
1.8 | update the CRUD of tasks By Mongo | 5 | Orabi | mayar | Abdelrhman Khaled
1.9 | update the CRUD of room By Mongo | 5 | Orabi | Ahmed Hashem | Mayar
2 | update the CRUD of training-program By Mongo | 5 | mahmoud ESlam | Abdelrahman Badr | Mahmoud Hashem
2.1 | update the CRUD of certificates By Mongo | 5 | mahmoud ESlam | Abdelrahman Badr | Mahmoud Hashem
2.2 | update the CRUD of master-Class By Mongo | 5 | Mahmoud Hashem | Abdelrahman Badr | mahmoud ESlam
2.3 | update the CRUD of educators By Mongo | 5 | Mahmoud Hashem | Abdelrahman Badr | mahmoud ESlam
2.4 | Change Task-Consulted to an array called Consultancies because of Mongo's structure and make CRUD with Mongo of Consultancies | 7 | Abdelrhman Khaled | mayar | Orabi
2.5 | update the CRUD of Notification By Mongo | 5 | nada | Karim Tamir | Marina
2.6 | update the CRUD of Course-Request By Mongo | 5 | nada | Karim Tamir | Marina
2.7 | CRUD Admin | 8 | Badr | Mahmoud Hashem | Mahmoud Eslam
2.8 | Create and Update Partner | 4 | Ahmed Hashem | mayar | Abdelrhman Khaled
2.9 | Create and Update a Member | 4 | karim | nada | Marina
3 | Show all Courses of educationl Center | 1 | Ahmed Hashem | mayar | Orabi
3.1 | Show all educators of educationl Center | 1 | Ahmed Hashem | Orabi | Abdelrhman Khaled
3.2 | Show all rooms of educationl Center | 1 | Abdelrhman Khaled | Ahmed Hashem | Orabi
3.3 | Show all master Class of educationl Center | 1 | Mayar | Orabi | Ahmed Hashem
3.4 | Show all certificates of educationl Center | 1 | marina | nada | Karim Tamir
3.5 | Show all training-programs of educationl Center | 1 | orabi | Abdelrhman Khaled | Mayar
3.6 | As a member I can create a link of a project I just finished along with project's details of sender and reciver to a partner | 2 | nada | Karim Tamir | Marina
3.7 | Delete and Update a project (link, reciver and sender details) | 4 | karim | nada | Marina